## Sheet1
KEY
CCDHB Variance Response Management (VRM) annual work plan 2020/21 Endorsed CCDM Council ........ |  | Activity scheduled
Activity completed
Activity on schedule
Activity 30 days behind plan
Activity 60 days behind plan
Activity greater than 90 days behind plan
|  | Variance Response Management Annual Work Plan 2019/20 |  |  | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
|  | Key activities | Key resource required | Accountability
CCDM | 1 | Implementation of CaaG screens in all inpatient areas | ICT, DSU, CCDM team, IOC team, VRM work stream | VRM work stream; CCDM Council
| 2 | Complete development of CaaG screen and varaince indicator scoring (VIS) system | ICT, DSU, CCDM team, IOC team, VRM work stream | VRM work stream; CCDM Council
| 3 | Implement Variance indicator scoring (VIS) mobile app with standard operating procedure | ICT, DSU, CCDM team, IOC team, VRM work stream | VRM work stream; CCDM Council | bar: AUG
| 4 | Ensure visibility of all acute and elective services - patient flow, bed capacity and staffing resource | ICT, DSU, CCDM team, IOC team, VRM work stream | VRM work stream
| 5 | Review of daily bed meetings - 9.15am; 6.00pm; 11.00pm Consideration of high level organisational meeting prior to daily 9.15am bed meeting | ICT, DSU, CCDM team, IOC team, VRM work stream | VRM work stream; IOC Manager and Nurse Manager | bar: AUG to SEP
Phase 2 of CaaG development - see requirements document | bar: AUG to OCT
Escalation plans - area specific as required Mental Health - ICU - work halted (awaiting VIS) NICU - Child Health - work halted (awaiting VIS) Theatres - work halted (awaiting VIS) | bar: AUG to SEP
| 10 | Quarterly reviews of ED and maternity esclation plans | Area specific; CCDM team | All specified areas - CNM/Ms; Operations Managers | bar: OCT; JAN; APR
| 12 | Continue weekly 'week that was' meetings | CCDM team; IOC team; VRM work stream | CCDM team; IOC team; VRM work stream
IOC/Bureau | 13 | Continuous recruitment of bureau staff - RNs; ENs; RMs; HCAs; MHSW | IOC manager; IOC nurse manager | IOC Manager; IOC Nurse Manager
Education | 15 | Education requirement for VIS organisation wide - tools; processes; use; interpretation; standard operating procedures; varaince response staff | IT; DSU; CCDM team; IOC team | CCDM team; VRM work stream | bar: AUG to SEP
| 16 | Ongoing education for duty nurse managers (DNM) and IOC team - TrendCare; CapPlan; VIS; SOPs; bureau allocation tool; CCDM | IT; DSU; CCDM team; IOC team | CCDM team; VRM work stream