## TrendCare Work Plan 2019-20
KEY
Activity scheduled
Activity completed
Activity on schedule
Activity 30 days behind plan
Activity 60 days behind plan
Activity greater than 90 days behind plan
2020
|  | TrendCare Annual Work Plan 2019/20 |  |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL
|  | Key activities | Key resource required | Accountability
GOVERNANCE | 1 | Review TC Operations Group TOR | Operational group | Operational group | bar: JAN; 2020 JAN to 2020 FEB
| 2 | Monitor TrendCare resource to ensure resource meets required demand | TrendCare coordinator | TrendCare coordinator
| 3 | Action Register for CCDM Council to be developed and utilised | CCDM council | CCDM council | bar: JAN
| 4 | Review TrendCare Business Rules | Operational group | IOC Director/Manager | bar: AUG to SEP
| 5 | Fortnightly meetings with CNM/M's and Kenepuru weekly visits | TrendCare coordinator | TrendCare coordinator
| 6 | Implement TC champions in each area | TrendCare coordinator | TrendCare coordinator
| 7 | TrendCare Expansion Plan (See numbers 32-39) | TrendCare coordinator | TrendCare coordinator | DEC: Revised
MAINTENANCE | 8 | Monthly Maintenance (See Plan) | TrendCare coordinator | TrendCare coordinator
| 9 | Upgrade TC Version within 3 months of release | CCDM council | IOC Director/Manager
| 10 | Monthly updates to CCDM Council of vendor movements | TrendCare coordinator | TrendCare coordinator
| 11 | TrendCare accuracy checks in readiness for FTE Calculations | TrendCare coordinator | TrendCare coordinator
GOLD STANDARDS | 12 | IRR Testing | TrendCare coordinator | TrendCare coordinator | NOV: Halted - awaiting upgrade; 2020 JAN: In progress
| 13 | Data sharing for all users | Local data councils | CCDM Team
| 14 | Annual assessment against Gold Standards | TrendCare coordinator | TrendCare coordinator | bar: DEC to 2020 MAY
| 15 | Submitting our data to be included in TC Benchmarking | TrendCare coordinator | TrendCare coordinator | bar: JUN
CCDM STANDARD 2 | 16 | Review of Annual Work Plan at each TrendCare Operational Group Meeting | Operational group | Operational group
| 17 | Monthly report to CCDM Council | TrendCare coordinator | TrendCare coordinator
EDUCATION | 18 | Provide introduction education to new Graduate Nurses and Midwives | TrendCare coordinator | Trendcare coordinator | 2020 JAN: Not done; 2020 FEB: Opportunity at this orientation has been withdrawn
| 19 | Provide one on one education to new CNM/M/ Operations Managers/ DNM's | Trendcare coordinator | Trendcare coordinator
| 20 | IRR refresher sessions as required | TrendCare coordinator | TrendCare coordinator | bar: JAN to MAR; OCT to NOV; 2020 JAN to 2020 MAR
| 21 | Mental Health Education (See MH Implementation Plan) | TrendCare coordinator | TrendCare coordinator
| 22 | Attend regular Educator meetings (senior nurse and midwife meetings) | TrendCare coordinator | TrendCare coordinator
| 23 | Refresher resource for all users available on ConnectMe | TrendCare coordinator | TrendCare coordinator | bar: JAN to APR; NOV to 2020 MAY
| 24 | Upgrade education as required ( Release date TBC by vendor) | TrendCare coordinator | TrendCare coordinator / TrendCare Australia
| 25 | Allocate Staff Screen Improvements | TrendCare coordinator | TrendCare coordinator
| 26 | Specialist Nurse Intervention Register | TrendCare coordinator | TrendCare coordinator | bar: JUL to 2020 MAY
| 27 | End of shift questionaires | Operational group | Operational group | bar: MAY to 2020 MAY
| 28 | Handover sheet implementation TWOM and DLV Suite | TrendCare coordinator | TrendCare coordinator | bar: AUG to 2020 MAY
| 29 | Discharge Analysis Improvements | TrendCare coordinator | TrendCare coordinator
CLINICAL SUPPORT | 30 | MCC Improvement Plan (5N, 5S, EDOU, MAPU, KENEPURU | TrendCare coordinator | TrendCare coordinator | bar: JAN to MAY
| 31 | Mental Health Improvement Plans for Nga Taiohi & Te Whare o Matairrangi | TrendCare coordinator | TrendCare coordinator
| 32 | Maternity Timing Studies | Maternity Services | Maternity Services | bar: APR to JUN
| 33 | Predictions by 09:15 Improvements | TrendCare coordinator | TrendCare coordinator
IMPLEMENTATION | 34 | Transit Lounge | TrendCare coordinator | TrendCare coordinator | bar: FEB
| 35 | Childrens Day Ward | TrendCare coordinator | TrendCare coordinator | bar: FEB
| 36 | Wellington Blood and Cancer Centre | TrendCare coordinator | TrendCare coordinator | DEC: Planned for July/Aug 2020 in line with MOSAIQ
| 37 | Medical Day Ward Kenepuru | TrendCare coordinator | TrendCare coordinator | bar: JUL to NOV
| 38 | PACU | TrendCare coordinator | TrendCare coordinator | bar: MAY to JUN
| 39 | IRU | TrendCare coordinator | TrendCare coordinator | bar: AUG to 2020 MAY
| 40 | Pacific Health Unit | TrendCare coordinator | TrendCare coordinator | bar: FEB
| 41 | Dialysis Units x2 | TrendCare coordinator | TrendCare coordinator | bar: JUN to JUL
| 42 | Mental Health Implementation Plan (See Plan) | TrendCare coordinator | TrendCare coordinator | NOV: Implementation complete

## TrendCare Work Plan 2020-21
KEY
Activity scheduled
Activity in progress
2020/21 |  | Activity complete
Activity >30 days behind schedule
Activity >60 days behind schedule
Activity >90 days behind schedule
[5 empty] | 2020 | [5 empty] | 2021
|  | TrendCare Annual Work Plan 2020/21 |  |  | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV
|  | Key activities | Key resource required | Accountability
GOVERNANCE | 1 | Review TC Operations Group TOR | Operational group | Operational group | bar: 2020 JUL; 2021 MAR to 2021 MAY
| 2 | Monitor TrendCare resource to ensure resource meets required demand | CCDM programme manager | CCDM Council | 2021 JAN: Issues raised to CCDM Council
| 3 | Action Register for TrendCare operational group maintained | TrendCare coordinator | Operational group | bar: 2020 JUL to 2021 JUN
| 4 | Review TrendCare business rules | Operational group | Operational group | bar: 2020 AUG to 2021 MAY
| 5 | Continue recruitment of TrendCare champions in all wards at a ratio of 1:10 | TrendCare coordinator | TrendCare coordinator | bar: 2020 JUL to 2021 JUN
| 6 | Develop role for TrendCare champions | TrendCare coordinator | Operational group | bar: 2020 JUL to 2021 MAY
| 7 | Review Annual Work Plan at each TrendCare Operational Group Meeting | Operational group | Operational group | bar: 2020 JUL to 2021 MAY
| 8 | Attend monthly SSHW Unit teleconferences | TrendCare coordinator | TrendCare coordinator | bar: 2020 JUL to 2021 MAY
| 9 | Monthly report to CCDM Council | TrendCare coordinator | CCDM programme manager | bar: 2020 JUL to 2021 MAY
| 10 | TrendCare Expansion Plan (See numbers 32-39) | TrendCare coordinator | CCDM programme manager/CCDM Council | bar: 2020 JUL to 2021 JUN
| 11 | Attend monthly vendor teleconferences | TrendCare coordinator | TrendCare coordinator | bar: 2020 JUL to 2021 JUN
| 12 | Review and refine monthly maintenance plan | TrendCare coordinator | Operational group | bar: 2020 JUL to 2020 NOV; 2021 JAN to 2021 MAY
MAINTENANCE | 13 | Implement and monitor monthly maintenance plan | TrendCare coordinator | Operational group | bar: 2020 JUL to 2021 JUN
| 14 | Implement TrendCare upgrades 3 months of release (dates awaited) | TrendCare coordinator | CCDM programme manager/CCDM Council | 2020 NOV: Release; 2021 NOV: Release
| 15 | Implement Cherwell for TrendCare requests | TrendCare coordinator | CCDM programme manager | bar: 2020 JUL; 2020 SEP; 2020 NOV to 2021 MAY
| 16 | Monthly updates to CCDM Council of vendor movements | CCDM programme manager | CCDM programme manager | bar: 2020 JUL to 2021 JUN
GOLD STANDARDS | 17 | TrendCare accuracy checks in readiness for FTE Calculations | TrendCare coordinator | CCDM programme manager | bar: 2020 JUL to 2021 JUN
| 18 | Annual IRR testing | TrendCare coordinator | CCDM programme manager | bar: 2021 JUN to 2021 AUG
| 19 | IRR testing for new staff within 2 weeks post orientation | TrendCare coordinator | TrendCare coordinator | bar: 2020 JUL to 2021 MAR; 2021 JUN to 2021 AUG
| 20 | Data sharing for all users | Local data councils | CCDM Team | bar: 2020 JUL to 2021 JUN
| 21 | Annual assessment against Gold Standards | TrendCare coordinator | Operational group | bar: 2020 SEP; 2020 NOV to 2021 MAY
| 22 | Benchmarking data to be shared with vendor for international study | TrendCare coordinator | CCDM programme manager | bar: 2020 JUL
EDUCATION | 23 | Investigate opportunity to provide introduction education to new graduate nurses and midwives and NESPS | TrendCare coordinator | TrendCare coordinator | bar: 2020 JUL to 2021 FEB
| 24 | Provide one on one education to new CNM/M/ Operations Managers/ DNM's | Trendcare coordinator | Trendcare coordinator | bar: 2020 JUL to 2021 JUN
| 25 | IRR refresher sessions as required | TrendCare coordinator | TrendCare coordinator | bar: 2021 FEB to 2021 MAY
| 26 | Attend ward core study days | TrendCare coordinator | TrendCare coordinator | bar: 2020 JUL to 2021 JUN
| 27 | Resources for all users available on ConnectMe | TrendCare coordinator | TrendCare coordinator | bar: 2020 JUL to 2021 MAY
| 28 | Continue face to face education sessions | TrendCare coordinator | TrendCare coordinator | bar: 2020 JUL to 2021 JUN
| 29 | Develop online education sessions | TrendCare coordinator | TrendCare coordinator | bar: 2020 AUG to 2021 MAY
| 30 | Develop champion education sessions | TrendCare coordinator | TrendCare coordinator | bar: 2020 AUG to 2020 NOV; 2021 JAN to 2021 MAY
| 31 | Upgrade education as required | TrendCare coordinator | TrendCare coordinator | bar: 2021 APR to 2021 MAY
CLINICAL SUPPORT | 32 | Continue with weekly TrendCare statistics | TrendCare coordinator | TrendCare coordinator | bar: 2020 JUL to 2021 JUN
| 33 | Regular meetings with CNM/M's and team leaders as appropriate | TrendCare coordinator | TrendCare coordinator | bar: 2020 JUL to 2021 JUN
| 34 | Minumum staffing requirements for TrendCare | CCDM programme manager | CCDM programme manager | bar: 2020 SEP to 2020 NOV; 2021 JAN to 2021 MAY
EXPANSION PLAN | 35 | Specialist Nurse Intervention Register - CNS/CMS | TrendCare coordinator | CCDM programme manager | 2020 DEC: Pilot
| 36 | Paediatric oncology | TrendCare coordinator | CCDM programme manager
| 37 | Emergency Department | TrendCare coordinator | CCDM programme manager | 2021 JAN: Pilot
| 38 | Urology | TrendCare coordinator | CCDM programme manager
| 39 | Gastroenterology | TrendCare coordinator | CCDM programme manager
| 40 | Te Mahoe | TrendCare coordinator | CCDM programme manager
| 41 | Dialysis Unit - Hutt | TrendCare coordinator | CCDM programme manager | bar: 2020 DEC to 2021 JAN
| 42 | Wellington Blood and Cancer Centre | TrendCare coordinator | CCDM programme manager | bar: 2021 JUN
| 43 | Medical Day Ward Kenepuru | TrendCare coordinator | CCDM programme manager | bar: 2021 JUN
| 44 | IRU | TrendCare coordinator | CCDM programme manager | bar: 2021 JUN
| 45 | Outpatients areas | TrendCare coordinator | CCDM programme manager
| 46 | District and community nurses and midwives | TrendCare coordinator | CCDM programme manager | 2020 DEC: Pilot

## RiskRegister (hidden)
DHB CCDM 17-18 Workplan - Issues register
No. | Date Raised | Description | Impact on CCDM | Mitigation Owner | Mitigation Strategy | Current Status
1 | 2017-06-02 | Poor attendace at the council meetings | High | Council chair, Union | Ask members to send representatives if they can't attend | Ongoing
2 | 2017-07-15 | 3.5.2 Implementation delayed due to high volume of work in IT dept. | Medium | CEO | Reprioritise IT workload | Ongoing